## Guide
Workflow for scrum practices
Note: Sprint review and retrospective for the last week is done during the demonstration.
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points (next module)
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Product Backlog
Team 11 Product Backlog
ID | User Story | Story Points | Priority
1 | Have a good looking welcome page
2 | Well organized and succinct pages
3 | Nice header with hamburger menu, social media links and login
4 | Footer with links to privacy and terms with hours and contact info
5 | Bottle service page leading to phone number and tickets page
6 | Tickets page with form to purchase event tickets
7 | About Us page with contact links
8 | Dress code page
9 | Careers page with form to submit CV
10 | Contact Us page with form for customers to reach out
11 | Music button for page
12 | Bottle service menu with prices and contact info
13 | Viewers should be able to see upcoming events
14 | Website should be dynamic
15 | Website should have fancy features
16 | Users should be able to create an account
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Sprint 1 Planning Meeting
Sprint Planning
Sprint | Participants
Sprint1 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Location: Online | Attended | Attended | Attended
Date: Feb. 10, 21 | Suomi | Greece | Hungary
Sprint 2 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Location: Online
Date: Feb. 17, 21
Sprint 3 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Location: Online
Date: Feb. 24, 21
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## Sprint 1 Backlog
Sprint Backlog : Sprint 1
ID | BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
1 | Build .php file with html and bootstrap | 1
1 | Build list of navigation links | 1
1 | Put navigation links in Hamburger menu | 2
3 | Set layout for welcome page | 1
3 | Select picture for welcome page | 1
3 | Set text for welcome page | 1
4 | Create header and footer for nav destination pages as frame.php | 2
4 | include frame.php in contact us and our contact info | 1
5 | Legalities tab: terms, privacy, accessibility options | 1
6 | Create subscribe box for users to sign up for newsletter and company info, events, etc | 2
6 | Display above footer in every page (add to frame.php) | 1
6 | Create database to hold these email addresses, match with other databases | 2
7 | Create page with menus displaying full menus | 1
8 | Create social media links and make easily visible | 1
8 | Add to frame.php | 1
9 | Create a registration / login link from main nav links | 1
9 | Create database for registrations | 2
9 | Link database for registrations | 2
9 | Create display php page for registration (consider pop-up) | 3
10 | Create careers page | 1
10 | Include form to send info and attach resume | 2
10 | Create database to handle data | 2
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0

## Sprint Review
Sprint Review: meeting 1
Sprint | Participants
Sprint 1 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Online | Online | Online | Online
Sprint 2 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Online
Sprint 3 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Online
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
2-hour prep time rule
No slides
Whole team participates
Invite the world
Summary of the meeting that includes decisions you made.
Sprint 1: Sprint planning: Completed successfully as a team. Tasks were distributed based on selection, dividing the 5 user stories into 4 tasks each.
Daily sprints: Scrum master Oluwole made sure daily sprints were 15 minutes maximum. Next user story tasks were chosen at the end of daily sprints and documented in Meeting Minutes along with completed tasks.
Sprint review: Teamwork has been presented, corrections have been applied based on user story requirements.
Sprint retrospective: All teammates were punctual regarding sprint meeting attendance. Tasks were completed on schedule. Sprint accomplished on schedule. Started 30 Nov 2020, finished 4 Dec 2020.
Sprint is signed off, next sprint begins Monday 7 Dec, 2020.
Sprint Planning Meeting: 16:00 EET
Location: Online

## Retrospective
Just discuss in your team, no documentation required
Sprint retrospective
Periodically take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
ScrumMaster
Product owner
Team
Possibly customers and others